## Title
PALM BEACH COUNTY SCOPE & FEE
HOUR ESTIMATION
Date:

## Project Information
Project Number:
Name of Prime / Subconsultant: | Enter name of prime or subconsultant
Project Description: | Enter project name & description
Project Length: |  |  | Feet
Number of Lanes:
Project Type: |  | (Minor / Major)
Proposed Design Contract Time: |  | months/days |  | Date of Negotiation: | Context Classification:

## Summary
Project Summary
Project Staff Hours
Activity No. | Activity | Enter Prime Name | Enter Name Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6 | Total Hours
1 | General Tasks | 0 | [6 empty] | 0
2 | Roadway Analysis | 0 | [6 empty] | 0
3 | Roadway Plans | 0 | [6 empty] | 0
4 | Drainage Analysis | 0 | [6 empty] | 0
5 | Drainage Plans | 0 | [6 empty] | 0
6 | Permits & Environmental | 0 | [6 empty] | 0
7 | Utilities | 0 | [6 empty] | 0
8 | Signing & Pavement Marking Analysis | 0 | [6 empty] | 0
9 | Signing & Pavement Marking Plans | 0 | [6 empty] | 0
10 | Signalization Analysis | 0 | [6 empty] | 0
11 | Signalization Plans | 0 | [6 empty] | 0
12 | Lighting Analysis | 0 | [6 empty] | 0
13 | Lighting Plans | 0 | [6 empty] | 0
14 | Survey - Field | 0 | [6 empty] | 0
15 | Survey Plans | 0 | [6 empty] | 0
16 | Survey - Right-of-Way | 0 | [6 empty] | 0
17 | Geotechnical | 0 | [6 empty] | 0
18 | Reimburseables | 0 | [6 empty] | 0
19 | Structures - Summary, Misc. Tasks, Dwgs. | 0 | [6 empty] | 0
20 | Bridge Development Report | 0 | [6 empty] | 0
21 | Short Span Concrete Bridge | 0 | [6 empty] | 0
22 | Medium Span Concrete Bridge | 0 | [6 empty] | 0
23 | Structural Steel Bridge | 0 | [6 empty] | 0
24 | Movable Span | 0 | [6 empty] | 0
25 | Retaining Walls | 0 | [6 empty] | 0
26 | Miscellaneous Structures | 0 | [6 empty] | 0
27 | Landscape Analysis | 0 | [6 empty] | 0
28 | Landscape Plans | 0 | [6 empty] | 0
29 | Architectural | 0 | [6 empty] | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 1. General Tasks
Project Activity 1: General Tasks
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
1.1 | Public Involvement | LS | 1 | 0 | 0
1.2 | Renderings and Fly Throughs | EA | 0 | 0 | 0
1.3 | PowerPoint Presentation | EA | 0 | 0 | 0
1.4 | Public Meeting Preparations | EA | 0 | 0 | 0
1.5 | Public Meeting Attendance/Followup | EA | 0 | 0 | 0
1.6 | Value Engineering Review | LS | 1 | 0 | 0
1.7 | Post Design Services | LS | 1 | 0 | 0 | Optional Services
1.8 | Railroad, Transit, and/or Airport Coordination | LS | 1 | 0 | 0
1.9 | Project Manager Coordination Meetings | EA | 0 | 0 | 0 | (LIST)
1. General Tasks Total |  |  |  |  | 0

## 2. Roadway Analysis
Project Activity 2: Roadway Analysis
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
2.1 | Typical Section Package | LS | 1 | 0 | 0
2.2 | Horizontal /Vertical Master Design Files | LS | 1 | 0 | 0
2.3 | Roundabout Design Analysis | LS | 1 | 0 | 0
2.4 | Design Report | EA | 0 | 0 | 0
2.5 | Computation Book & Quantities | EA | 0 | 0 | 0 | (LIST Submittals)
2.6 | Cost Estimate | EA | 0 | 0 | 0 | (LIST Submittals)
2.7 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0 | Optional Services
2.8 | ROW Impact Analysis | LS | 1 | 0 | 0
2.9 | Other Roadway Analyses | LS | 1 | 0 | 0
2.1 | Monitor Existing Structures | LS | 1 | 0 | 0
2.11 | Field Review | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
2.12 | Technical Meetings | EA | 0 | 0 | 0 | (LIST)
2. Roadway Analysis Total |  |  |  |  | 0

## 3. Roadway Plans
Project Activity 3: Roadway Plans
Task No. | Task | Units | No. of Units or Sheet | Hours/ Unit or Sheet | Total Hours | Comments
3.1 | Key Sheet | Sheet | 0 | 0 | 0
3.2 | Typical Sections | EA | 0 | 0 | 0
3.3 | Typical Section Details | EA | 0 | 0 | 0
3.4 | General Notes/Pay Item Notes/Summary of Quantities | Sheet | 0 | 0 | 0
3.5 | Project Control Sheet – Survey Plans | Sheet | 0 | 0 | 0
3.6 | Master Plan | Sheet | 0 | 0 | 0
3.7 | Plan/Profile Sheet | Sheet | 0 | 0 | 0
3.8 | Profile Sheet | Sheet | 0 | 0 | 0
3.9 | Plan Sheet | Sheet | 0 | 0 | 0
3.10 | Driveway Profiles | EA | 0 | 3 | 0
3.11 | Special Profiles | Sheet | 0 | 0 | 0
3.12 | Back-of-Sidewalk Profile Sheet | Sheet | 0 | 0 | 0
3.13 | Intersection Layout Details | Sheet | 0 | 0 | 0
3.14 | Plateau Intersection Detail | Sheet | 0 | 0 | 0
3.15 | Miscellaneous Details | EA | 0 | 0 | 0
3.16 | Right-of-Way Acquisition Exhibit | Sheet | 0 | 0 | 0
3.17 | Roadway Soil Survey Sheets | Sheet | 0 | 0 | 0
3.18 | Railroad Detail Sheets | Sheet | 0 | 0 | 0
3.19 | Cross Sections | EA | 0 | 3 | 0
3. Roadway Plans Total |  |  |  |  | 0

## 4. Drainage Analysis
Project Activity 4: Drainage Analysis
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
4.1 | Drainage Map Hydrology | LF | 0 | 0 | 0
4.2 | Determine Base Clearance Water Elevation | EA | 0 | 0 | 0
4.3 | Pond Siting Analysis and Report | EA | 0 | 0 | 0
4.4 | Design of Cross Drains | EA | 0 | 0 | 0
4.5 | Design of Roadside Ditches | LF | 0 | 0 | 0
4.6 | Design of Storm Drains | EA | 0 | 0 | 0
4.7 | French Drain Systems | LF | 0 | 0 | 0
4.8 | Drainage Design Report | LS | 1 | 0 | 0
4.9 | Bridge Hydraulic Report | EA | 0 | 0 | 0
4.1 | Technical Special Provisions / Modified Special Provisions | LS | 1 | 0 | 0 | Optional Services
4. Drainage Analysis Total |  |  |  |  | 0

## 5. Drainage Plans
Project Activity 5: Drainage Plans
Task No. | Task | Scale | Units | No. of Units or Sheet | Hours/ Unit or Sheet | Total Hours | Comments
5.1 | Drainage Area Map |  | Sheet | 0 | 0 | 0
5.2 | Box Culvert Detail Sheet |  | Sheet | 0 | 0 | 0
5.3 | Drainage Structure |  | EA | 0 | 3 | 0
5.4 | Miscellaneous Drainage Detail Sheets |  | Sheet | 0 | 0 | 0
5.5 | Lateral Ditch Plan/Profile |  | LF | 0 | 0 | 0
5.6 | Lateral Ditch Cross Sections |  | EA | 0 | 0 | 0
5.7 | Retention/Detention Ponds Detail Sheets |  | Sheet | 0 | 0 | 0
5.8 | Retention Pond Cross Sections |  | EA | 0 | 0 | 0
5.9 | SWPPP Sheets |  | Sheet | 0 | 0 | 0
5. Drainage Plans Total | [5 empty] | 0

## 6. Permits & Environmental
Project Activity 6: Permits & Environmental
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
6.1 | Pond Site Alternatives | EA | 0 | 0 | 0
6.2 | Establish Wetland Jurisdictional Lines | LS | 1 | 0 | 0
6.3 | Existing Permit Analysis | LS | 1 | 0 | 0
6.4 | Complete and Submit All Required Permit Applications | EA | 0 | 0 | 0 | (LIST)
6.5 | Prepare Dredge and Fill Sketches | LS | 1 | 0 | 0
6.6 | Mitigation Coordination and Meetings | EA | 0 | 0 | 0 | (LIST)
6.7 | Technical Meetings | EA | 0 | 0 | 0 | (LIST)
6. Permits and Environmental Total |  |  |  |  | 0

## 7. Utilities
Project Activity 7: Utilities
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
7.1 | Incorporate Existing Utiltiy Facilities | EA | 0 | 0 | 0
7.2 | Conflict Matrix | EA | 0 | 0 | 0
7.3 | Identify and Incorporate Conflict Resolutions | LS | 1 | 0 | 0
7.4 | Meetings | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
7. Utilities Total |  |  |  |  | 0

## 8. Signing & Marking Analysis
Project Activity 8: Signing & Marking Analysis
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
8.1 | Master Design Files | LS | 1 | 0 | 0
8.2 | Quantities | EA | 0 | 0 | 0 | (LIST Submittals)
8.3 | Cost Estimate | EA | 0 | 0 | 0 | (LIST Submittals)
8.4 | Other Signing and Pavement Marking | LS | 1 | 0 | 0
8. Signing and Pavement Marking Analysis Total |  |  |  |  | 0

## 9. Signing & Marking Plans
Project Activity 9: Signing & Marking Plans
Task No. | Task | Units | No of Units | Hours/ Unit or Sheet | Total Hours | Comments
9.1 | Key Sheet | Sheet | 0 | 0 | 0
9.2 | General Notes/Pay Item Notes/Summary of Quantities | Sheet | 0 | 0 | 0
9.3 | Typical Details | EA | 0 | 0 | 0
9.4 | Plan Sheet | Sheet | 0 | 0 | 0
9. Signing and Pavement Marking Plans Total |  |  |  |  | 0

## 10. Signalization Analysis
Project Activity 10: Signalization Analysis
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
10.1 | Traffic Data Collection | LS | 1 | 0 | 0
10.2 | Traffic Data Analysis | PI | 0 | 0 | 0
10.3 | Signal Warrant Study | LS | 1 | 0 | 0
10.4 | System Timings | LS | 1 | 0 | 0
10.5 | Reference and Master Signalization Design File | PI | 0 | 0 | 0
10.6 | Reference and Master Interconnect Communication Design File | LS | 1 | 0 | 0
10.7 | Overhead Street Name Sign Design | EA | 0 | 0 | 0
10.8 | Pole Elevation Analysis | LS | 1 | 0 | 0
10.9 | Traffic Signal Operation Report | LS | 1 | 0 | 0
10.1 | Quantities | EA | 0 | 0 | 0 | (LIST Submittals)
10.11 | Cost Estimate | EA | 0 | 0 | 0 | (LIST Submittals)
10.12 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
10.13 | Other Signalization Analysis | LS | 1 | 0 | 0
10.14 | Field Reviews | EA | 0 | 0 | 0 | (LIST)
10.15 | Technical Meetings | EA | 0 | 0 | 0 | (LIST
10. Signalization Analysis Total |  |  |  |  | 0

## 11. Signalization Plans
Project Activity 11: Signalization Plans
Task No. | Task | Scale | Units | No of Units | Hours/ Unit or Sheet | Total Hours | Comments
11.1 | Key Sheet |  | Sheet | 0 | 0 | 0
11.2 | General Notes/Pay Item Notes |  | Sheet | 0 | 0 | 0
11.3 | Plan Sheet |  | Sheet | 0 | 0 | 0
11.4 | Interconnect Plans |  | Sheet | 0 | 0 | 0
11.5 | Traffic Monitoring Site |  | EA | 0 | 0 | 0
11.6 | Special Details |  | Sheet | 0 | 0 | 0
11.7 | Special Service Point Details |  | EA | 0 | 0 | 0
11.8 | Mast Arm/Monotube Tabulation Sheet |  | PI | 0 | 0 | 0
11.9 | Strain Pole Schedule |  | PI | 0 | 0 | 0
11.1 | TTCP Signal |  | EA | 0 | 0 | 0
11.11 | Temporary Detection Sheet |  | PI | 0 | 0 | 0
11.12 | Utility Conflict Sheet |  | Sheet | 0 | 0 | 0
11. Signalization Plans Total | [5 empty] | 0

## 12. Lighting Analysis
Project Activity 12: Lighting Analysis
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
12.1 | Lighting Justification Report | LS | 1 | 0 | 0
12.2 | Lighting Design Analysis Report (LDAR) | LS | 1 | 0 | 0
12.3 | Voltage Drop Calculations | EA | 0 | 0 | 0
12.4 | FDEP Coordination and Report | LS | 1 | 0 | 0
12.5 | Reference and Master Design Files | LS | 1 | 0 | 0
12.6 | Design Documentation | LS | 1 | 0 | 0
12.7 | Quantities | EA | 0 | 0 | 0 | (LIST Submittals)
12.8 | Cost Estimate | EA | 0 | 0 | 0 | (LIST Submittals)
12.9 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
12.1 | Other Lighting Analysis | LS | 1 | 0 | 0
12.11 | Field Reviews | EA | 0 | 0 | 0 | (LIST)
12.12 | Technical Meetings | EA | 0 | 0 | 0 | (LIST)
12. Lighting Analysis Total |  |  |  |  | 0

## 13. Lighting Plans
Project Activity 13: Lighting Plans
Task No. | Task | Scale | Units | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
13.1 | Key Sheet |  | Sheet | 0 | 0 | 0
13.2 | General Notes/Pay Item Notes |  | Sheet | 0 | 0 | 0
13.3 | Pole Data, Legend and Criteria |  | Sheet | 0 | 0 | 0
13.4 | Service Point Details |  | Sheet | 0 | 0 | 0
13.5 | Project Layout |  | Sheet | 0 | 0 | 0
13.6 | Plan Sheet |  | Sheet | 0 | 0 | 0
13.7 | Special Details |  | Sheet | 0 | 0 | 0
13. Lighting Plans Total | [5 empty] | 0

## 14. Survey - Field
Project Activity 14: Survey - Field
Task No. | Task | Units | No of Units | Hours/Unit | Total Hours | Comments
14.1 | Horizontal Project Control (HPC)
| 2-Lane Roadway | LF | 0 | 0 | 0
| Multi-lane Roadway | LF | 0 | 0 | 0
14.2 | Vertical PC / Bench Line
| 2-Lane Roadway | LF | 0 | 0 | 0
| Multi-lane Roadway | LF | 0 | 0 | 0
14.3 | Reference Points
| 2-Lane Roadway | EA | 0 | 0 | 0
| Multi-lane Roadway | EA | 0 | 0 | 0
14.4 | Baseline Layout | LF | 0 | 0 | 0
14.5 | Section, Subdivision & Property Ties | EA | 0 | 0 | 0
14.6 | Topography/DTM (3D) | LF | 0 | 0 | 0
14.7 | Cross Sections | EA | 0 | 0 | 0 | Width of ROW?
14.8 | Side Street Surveys | LF | 0 | 0 | 0
14.9 | SUE | EA | 0 | 0 | 0 | Optional Services (Upland/Submerged?)
14.1 | Locates - Pothole | EA | 0 | 0 | 0
14.11 | Outfall Survey | LF | 0 | 0 | 0
14.12 | Drainage Survey | EA | 0 | 0 | 0
14.13 | Bridge Survey | EA | 0 | 0 | 0 | Major or Minor?
14.14 | Canel Survey | LF | 0 | 0 | 0 | (Provide Description of canal condition - maintained?)
14.15 | Channel Survey and Soundings | LS | 1 | 0 | 0
14.16 | Pond Site Survey | EA | 0 | 0 | 0 | (Provide Description of site - How heavily forested?)
14.17 | Jurisdictional Line Survey | LS | 1 | 0 | 0 | (Detail - MHWL?)
14.18 | Tree Survey | LS | 1 | 0 | 0 | (Provide Description - How heavily forested?)
14.19 | Route/Corridor Survey | LF | 0 | 0 | 0
14.2 | Boundary Survey | LS | 1 | 0 | 0
14.21 | Topographic Survey | LS | 1 | 0 | 0
14.22 | Specific Purpose Survey | LS | 1 | 0 | 0
14.23 | Hydrographic Survey | LS | 1 | 0 | 0
14.24 | Quantity Survey | LS | 1 | 0 | 0
14.25 | Record/As-Built Survey | LS | 1 | 0 | 0
14.26 | R/W Staking
| Parcel | EA | 0 | 0 | 0
| R/W Line | LF | 0 | 0 | 0
14.27 | Meetings | EA | 0 | 0 | 0 | (LIST)
14. Survey - Field Total |  |  |  |  | 0

## 15. Survey Plans
Project Activity 15: Survey Plans
Task No. | Task | Units | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
15.1 | Alignment | LF | 0 | 0 | 0
15.2 | Section and 1/4 Section Lines | Section | 0 | 0 | 0
15.3 | Subdivisions / Property Lines | EA | 0 | 0 | 0
15.4 | Existing R/W | LF | 0 | 0 | 0
15.5 | Topography | LF | 0 | 0 | 0
15.6 | Parent Tract Properties/Existing Easements | EA | 0 | 0 | 0
15.7 | Title Review | LS | 1 | 0 | 0
15.8 | Jurisdictional/Agency Lines | LF | 0 | 0 | 0
15.9 | Survey Key Sheet | Sheet | 0 | 0 | 0
15.1 | Survey Detail & Legend Sheet | Sheet | 0 | 0 | 0
15.11 | Reference Point Sheet | Sheet | 0 | 0 | 0
15.12 | Project Control Sheet | Sheet | 0 | 0 | 0
15.13 | Specific Purpose & Topographic Survey | Sheet | 1 | 0 | 0
15.14 | Boundary Survey | EA | 0 | 0 | 0 | (LIST)
15.15 | Technical Meetings | EA | 0 | 0 | 0 | (LIST)
15. Survey Plans Total |  |  |  |  | 0

## 16. Survey - Right-of-Way
Project Activity 16: Survey - Right-of-Way
Task No. | Task | Units | No. of Units | Hours/ Unit or Sheet | $$/Unit | Total Hours | Comments
16.1 | R/W Procurement Map Key Sheet | Sheet | 0 | 0 |  | 0
16.2 | R/W Procurement Map Detail Sheet | Sheet | 0 | 0 |  | 0
16.3 | Prepare Right-of-Way Map | LS | 1 | 0 |  | 0
16.4 | Technical Meetings | EA | 0 | 0 |  | 0 | (LIST)
16.5 | Convert Legal Description & Sketch to a Boundary Survey | EA | 0 |  | 700 |  | Total to be listed on Expense Summary Sheet ("X" number of legal and sketches converted at $700 each)
16.6 | Legal Descriptions & Sketches | EA | 0 |  | 600 |  | Total to be listed on Expense Summary Sheet ("X" number of legal and sketches at $600 each)
16. Survey - Right-of-Way Total | [5 empty] | 0

## 17. Geotechnical
Project Activity 17: Geotechnical
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
Roadway
17.1 | Develop Detailed Boring Location Plan | LS | 1 | 0 | 0
17.2 | Stake Borings/Utility Clearance | Boring | 0 | 0 | 0
17.3 | Muck Probing | Crew Day | 0 | 0 | 0
17.4 | Coordinate and Develop MOT Plans for Field Investigation | EA | 0 | 0 | 0
17.5 | Drilling Access Permits | Location | 0 | 0 | 0
17.6 | Property Clearances | EA | 0 | 0 | 0
17.7 | Groundwater Monitoring | EA | 0 | 0 | 0
17.8 | LBR/Resilient Modulus Sampling | EA | 0 | 0 | 0
14.9 | Coordination of Field Work | 100 lf of boring | 0 | 0 | 0
17.10 | Soil and Rock Classification - Roadway | 100 lf of boring | 0 | 0 | 0
17.11 | Design LBR | LS | 1 | 0 | 0
17.12 | Laboratory Data | 100 lf of boring | 0 | 0 | 0
17.13 | Seasonal High Water Table | Boring | 0 | 0 | 0
17.14 | Parameters for Water Retention Areas | EA | 0 | 0 | 0
17.15 | Delineate Limits of Unsuitable Material | Cross-section | 0 | 0 | 0
17.16 | Electronic Files for Cross-Sections | 100 lf of boring | 0 | 0 | 0
17.17 | Embankment Settlement and Stability | Embankment Boring | 0 | 0 | 0
17.18 | Monitor Existing Structures | LS | 1 | 0 | 0
17.19 | Stormwater Volume Recovery and/or Background Seepage Analysis | EA | 0 | 0 | 0
17.20 | Geotechnical Recommendations | LS | 1 | 0 | 0
17.21 | Pavement Condition Survey and Pavement Evaluation Report | LS | 1 | 0 | 0
17.22 | Preliminary Roadway Report | LS | 1 | 0 | 0
17.23 | Final Report | EA | 0 | 0 | 0
17.24 | Auger Boring Drafting | 100 lf boring | 0 | 0 | 0
17.25 | SPT Boring Drafting | 100 lf boring | 0 | 0 | 0
Roadway Geotechnical Subtotal |  |  |  |  | 0
Structures
17.26 | Develop Detailed Boring Location Plan | LS | 1 | 0 | 0
17.27 | Stake Borings/Utility Clearance | Boring | 0 | 0 | 0
17.28 | Coordinate and Develop MOT Plans for Field Investigation | EA | 0 | 0 | 0
17.29 | Drilling Access Permits | Location | 0 | 0 | 0
17.30 | Property Clearances | EA | 0 | 0 | 0
17.31 | Collection of Corrosion Samples | EA | 0 | 0 | 0
17.32 | Coordination of Field Work | 100 lf of boring | 0 | 0 | 0
17.33 | Soil and Rock Classification - Structures | 100 lf of boring | 0 | 0 | 0
17.34 | Tabulation of Laboratory Data | 100 lf of boring | 0 | 0 | 0
17.35 | Estimate Design Groundwater Level for Structures | EA | 0 | 0 | 0
17.36 | Selection of Foundation Alternatives (BDR) | Bridge boring | 0 | 0 | 0
17.37 | Detailed Analysis of Selected Foundation Alternate(s) | Bridge boring | 0 | 0 | 0
17.38 | Bridge Construction and Testing Recommendations | Bridge boring | 0 | 0 | 0
17.39 | Lateral Load Analysis (Optional) | Bridge boring | 0 | 0 | 0
17.40 | Walls | Wall Boring | 0 | 0 | 0
17.41 | Sheet Pile Wall Analysis (Optional) | Wall Boring | 0 | 0 | 0
17.42 | Design Soil Parameters for Signs, Signals, High Mast Lights, and Strain Poles and Geotechnical Recommendations | Boring | 0 | 0 | 0
17.43 | Box Culvert Analysis | EA | 0 | 0 | 0
17.44 | Preliminary Report - BDR | EA | 0 | 0 | 0
17.45 | Final Report - Bridge and Associated Walls | EA | 0 | 0 | 0
17.46 | Final Reports - Signs, Signals, Box Culvert, Walls and High Mast Lights | EA | 0 | 0 | 0
17.47 | SPT Boring Drafting | 100 lf of boring | 0 | 0 | 0
17.48 | Other Geotechnical | LS | 1 | 0 | 0
Structural Geotechnical Subtotal |  |  |  |  | 0
17.49 | Technical Special Provisions and Modified Special Provisions | EA | 0 | 0 | 0
17.50 | Field Reviews | EA | 0 | 0 | 0 | (LIST)
17.51 | Technical Meetings | EA | 0 | 0 | 0 | (LIST)
17. Geotechnical Total |  |  |  |  | 0

## 18. Reimbursables
Project Activity 18: Reimbursables
Task No. | Task | Scale | Units | No. of Units | $$/Unit | Total Cost | Comments
18.1 | Prints for Submittals
| Plans | 11x17 | Sheet | 0 | 0 | 0
| Other | 8 1/2x 11 | Sheet | 0 | 0 | 0
18.2 | Permit Fee
| SFWMD |  | EA | 0 | 0 | 0 | (LIST - ERP, Water Use)
| LWDD |  | EA | 0 | 0 | 0 | (LIST - R/W, Utility, Bridge)
| ACOE |  | EA | 0 | 0 | 0
| Improvement District |  | EA | 0 | 0 | 0 | (LIST - ITID, NPBCID, SIRWCD, SID)
| Municipality |  | EA | 0 | 0 | 0 | (LIST)
| ERM |  | EA | 0 | 0 | 0 | (LIST)
18.3 | Other |  | LS | 1 | 0 | 0 | (Describe)
18. Reimbursables Total | [5 empty] | 0

## 19. Structures - Plans
Project Activity 19: Structural Plans
Task No. | Task | Units | No. of Units | Hours per Unit or Sheet | Total | Comments
19.1 | Key Sheet | Sheet | 0 | 0 | 0
19.2 | Index of Drawings | Sheet | 0 | 0 | 0
19.3 | Bridge Typical Section - Existing | EA | 0 | 0 | 0
19.4 | Bridge Typical Section - Proposed | EA | 0 | 0 | 0
19.5 | Project Layout | Sheet | 0 | 0 | 0
19.6 | General Notes and Bid Items | Sheet | 0 | 0 | 0
19.7 | Miscellaneous Details | EA | 0 | 0 | 0
19.8 | Incorporate Report of Core Borings | Sheet | 0 | 0 | 0
19.9 | Bridge Plans | LS | 1 | 0 | 0
19.1 | Existing Bridge Plans | LS | 1 | 0 | 0
19.11 | Temporary Bridge Plans | LS | 1 | 0 | 0
19.12 | Quantites | EA | 0 | 0 | 0 | (LIST Submittals)
19.13 | Cost Estimate | EA | 0 | 0 | 0 | (LIST Submittals)
19.14 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
19.15 | Retaining Walls | EA | 0 | 0 | 0
19.16 | Miscellaneous Structures | Sheet | 0 | 0 | 0
19.17 | Field Reviews | EA | 0 | 0 | 0 | (LIST)
19.18 | Technical Meetings | EA | 0 | 0 | 0 | (LIST)
19. Structures - Structural Plans Total |  |  |  |  | 0

## 20. Bridge Development Report
Project Activity 20: Bridge Development Report
Task No. | Task | Units | No of Units | Hours/ Unit or Sheet | Total Hours | Comments
General Requirement
20.1 | Bridge Geometry | LS | 1 | 0 | 0
20.2 | Ship Impact Data Collection | LS | 1 | 0 | 0
20.3 | Ship Impact Criteria | EA | 0 | 0 | 0
Superstructure Alternatives
20.4 | Short Span Concrete Bridge | EA | 0 | 0 | 0
20.5 | Medium Span Concrete Bridge | EA | 0 | 0 | 0
20.6 | Long Span Concrete Bridge | EA | 0 | 0 | 0
20.7 | Structural Steel Bridge | EA | 0 | 0 | 0
Foundation & Substructure Alternatives
20.8 | Pier/Bent | EA Type | 0 | 0 | 0
20.9 | Shallow Foundations / GRS Abutments | EA Type | 0 | 0 | 0
20.1 | Deep Foundations | EA Foundation Evaluated | 0 | 0 | 0
Movable Span
20.11 | Data Collection and Design Criteria | LS | 1 | 0 | 0
20.12 | Movable Span Geometrics and Clearances | LS | 1 | 0 | 0
20.13 | Deck System Evaluation | LS | 1 | 0 | 0
20.14 | Framing Plan Development | LS | 1 | 0 | 0
20.15 | Main Girder Preliminary Design | LS | 1 | 0 | 0
20.16 | Conceptual Span Balance/Counterweight | LS | 1 | 0 | 0
20.17 | Support System Development | LS | 1 | 0 | 0
20.18 | Drive Power Calculations | LS | 1 | 0 | 0
20.19 | Drive System Development | LS | 1 | 0 | 0
20.2 | Power and Control Development | LS | 1 | 0 | 0
20.21 | Conceptual Pier Design | LS | 1 | 0 | 0
20.22 | Foundation Analysis (FL PIER) | LS | 1 | 0 | 0
20.23 | Tender Visibility Study | LS | 1 | 0 | 0
Other BDR Issues
20.24 | Aesthetics | LS | 1 | 0 | 0
20.25 | TTCP/Staged Construction Requirements | LS | 1 | 0 | 0
20.26 | Constructibility Requirements | LS | 1 | 0 | 0
20.27 | Load Rating for damaged/widened structures | EA Unit | 0 | 0 | 0
20.28 | Quantity and Cost Estimates | EA | 0 | 0 | 0 | (LIST Submittals)
20.29 | Quantity and Cost Estimates - Movable Span | EA | 0 | 0 | 0 | (LIST Submittals)
20.3 | Wall Type Justification | LS | 1 | 0 | 0
Report Preparation
20.31 | Exhibits | EA SHEET | 0 | 0 | 0
20.32 | Exhibits - Movable Span | EA SHEET | 0 | 0 | 0
20.33 | Report Preparation | LS | 1 | 0 | 0
20.34 | Report Preparation - Movable Span | LS | 1 | 0 | 0
20.35 | BDR Submittal Package | LS | 1 | 0 | 0
20. Bridge Development Report Total |  |  |  |  | 0

## 21. Short Span Concrete Bridge
Project Activity 21: Short Span Concrete Bridge
Task No. | Task | Units | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
General Layout Design and Plans
21.1 | Overall Bridge Final Geometry | LS | 1 | 0 | 0
21.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 | 0
21.3 | General Plan and Elevation | Sheet | 0 | 0 | 0
21.4 | Construction Staging | Sheet | 0 | 0 | 0
21.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0
21.6 | Miscellaneous Details | Sheet | 0 | 0 | 0
End Bent Design and Plans
21.7 | End Bent Geometry | EA End Bent | 0 | 0 | 0
21.8 | End Bent Structural Design | EA Design | 0 | 0 | 0
21.9 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0
21.1 | End Bent Details | Sheet | 0 | 0 | 0
Intermediate Bent Design and Plans
21.11 | Bent Geometry | EA Bent | 0 | 0 | 0
21.12 | Bent Stability Analysis | EA Analysis | 0 | 0 | 0
21.13 | Bent Structural Design | EA Design | 0 | 0 | 0
21.14 | Bent Plan and Elevation | Sheet | 0 | 0 | 0
21.15 | Bent Details | Sheet | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
21.16 | Foundation Layout | Sheet | 0 | 0 | 0
Miscellaneous Superstructure Design and Plans
21.17 | Finish Grade Elevation Calculation | LS | 1 | 0 | 0
21.18 | Finish Grade Elevations | Sheet | 0 | 0 | 0
Cast-in-Place Slab Bridges
21.19 | Bridge Deck Design | EA Unit | 0 | 0 | 0
21.2 | Superstructure Plan | Sheet | 0 | 0 | 0
21.21 | Superstructure Sections and Details | Sheet | 0 | 0 | 0
Prestressed Slab Unit Bridges
21.22 | Prestressed Slab Unit Design | EA Design | 0 | 0 | 0
21.23 | Prestressed Slab Unit Layout | Sheet | 0 | 0 | 0
21.24 | Prestressed Slab Unit Details and Schedule | Sheet | 0 | 0 | 0
21.25 | Deck Topping Reinforcing Layout | Sheet | 0 | 0 | 0
21.26 | Superstructure Sections and Details | Sheet | 0 | 0 | 0
Reinforcing Bar List
21.27 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0
Load Rating
21.28 | Load Ratings | EA Unit | 0 | 0 | 0
21. Short Span Concrete Bridge Total |  |  |  |  | 0

## 22. Medium Span Concrete Bridge
Project Activity 22: Medium Span Concrete Bridge
Task No. | Task | Units | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
General Layout Design and Plans
22.1 | Overall Bridge Final Geometry | LS | 1 | 0 | 0
22.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 | 0
22.3 | General Plan and Elevation | Sheet | 0 | 0 | 0
22.4 | Construction Staging | Sheet | 0 | 0 | 0
22.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0
22.6 | Miscellaneous Details | Sheet | 0 | 0 | 0
End Bent Design and Plans
22.7 | End Bent Geometry | EA End Bent | 0 | 0 | 0
22.8 | Wingwall Design and Geometry | EA End Bent | 0 | 0 | 0
22.9 | End Bent Structural Design | EA Design | 0 | 0 | 0
22.1 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0
22.11 | End Bent Details | Sheet | 0 | 0 | 0
Intermediate Bent Design and Plans
22.12 | Bent Geometry | EA Bent | 0 | 0 | 0
22.13 | Bent Stability Analysis | EA Design | 0 | 0 | 0
22.14 | Bent Structural Design | EA Design | 0 | 0 | 0
22.15 | Bent Plan and Elevation | Sheet | 0 | 0 | 0
22.16 | Bent Details | Sheet | 0 | 0 | 0
Pier Design and Plans
22.17 | Pier Geometry | EA Pier | 0 | 0 | 0
22.18 | Pier Stability Analysis | EA Design | 0 | 0 | 0
22.19 | Pier Structural Design | EA Design | 0 | 0 | 0
22.2 | Pier Plan and Elevation | Sheet | 0 | 0 | 0
22.21 | Pier Details | Sheet | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
22.22 | Foundation Layout | Sheet | 0 | 0 | 0
Superstructure Deck Design and Plans
22.23 | Finish Grade Elevation (FGE) Calculation | LS | 1 | 0 | 0
22.24 | Finish Grade Elevations | Sheet | 0 | 0 | 0
22.25 | Bridge Deck Design | EA Section | 0 | 0 | 0
22.26 | Bridge Deck Reinforcing and Concrete Quantities | EA Unit | 0 | 0 | 0
22.27 | Diaphragm Design | EA Section | 0 | 0 | 0
22.28 | Superstructure Plan | Sheet | 0 | 0 | 0
22.29 | Superstructure Section | Sheet | 0 | 0 | 0
22.3 | Miscellaneous Superstructure Details | Sheet | 0 | 0 | 0
Reinforcing Bar Lists
22.31 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0
Continuous Concrete Girder Design
22.32 | Section Properties | LS | 1 | 0 | 0
22.33 | Material Properties | LS | 1 | 0 | 0
22.34 | Construction Sequence | EA Unit | 0 | 0 | 0
22.35 | Tendon Layouts | EA Unit | 0 | 0 | 0
22.36 | Live Load Analysis | EA Unit | 0 | 0 | 0
22.37 | Temperature Gradient | EA Unit | 0 | 0 | 0
22.38 | Time Dependent Analysis | EA Unit | 0 | 0 | 0
22.39 | Stress Summary | EA Unit | 0 | 0 | 0
22.4 | Ultimate Moments | EA Unit | 0 | 0 | 0
22.41 | Ultimate Shear | EA Unit | 0 | 0 | 0
22.42 | Construction Loading | EA Unit | 0 | 0 | 0
22.43 | Framing Plan | Sheet | 0 | 0 | 0
22.44 | Girder Elevation, including Grouting Plan and Vent Locations | Sheet | 0 | 0 | 0
22.45 | Girder Details | Sheet | 0 | 0 | 0
22.46 | Erection Sequence | Sheet | 0 | 0 | 0
22.47 | Splice Details | Sheet | 0 | 0 | 0
22.48 | Girder Deflections and Camber | Sheet | 0 | 0 | 0
Simple Span Concrete Design
22.49 | Prestressed Beam | EA Design | 0 | 0 | 0
22.5 | Prestressed Beam Schedules | Sheet | 0 | 0 | 0
22.51 | Framing Plan | Sheet | 0 | 0 | 0
Beam Stability
22.52 | Beam/girder stability | EA Unit | 0 | 0 | 0
Bearing
22.53 | Bearing pad and bearing plate design | Type/ Span | 0 | 0 | 0
22.54 | Bearing pad and bearing plate details | Sheet | 0 | 0 | 0
Load Rating
22.55 | Load Ratings | Per Beam | 0 | 0 | 0
22. Medium Span Concrete Bridge Total |  |  |  |  | 0

## 23. Structural Steel Bridge
Project Activity 23: Structural Steel Bridge
Task No. | Task | Unit | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
General Layout Design and Plans
23.1 | Overall Bridge Final Geometry | LS | 1 | 0 | 0
23.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 | 0
23.3 | General Plan and Elevation | Sheet | 0 | 0 | 0
23.4 | Construction Staging | Sheet | 0 | 0 | 0
23.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0
23.6 | Miscellaneous Details | Sheet | 0 | 0 | 0
End Bent Design and Plans
23.7 | End Bent Geometry | EA Bent | 0 | 0 | 0
23.8 | Wingwall Design and Geometry | EA Bent | 0 | 0 | 0
23.9 | End Bent Structural Design | EA Design | 0 | 0 | 0
23.1 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0
23.11 | End Bent Details | Sheet | 0 | 0 | 0
Intermediate Bent Design and Plans
23.12 | Bent Geometry | EA bent | 0 | 0 | 0
23.13 | Bent Stability Analysis | EA design | 0 | 0 | 0
23.14 | Bent Structural Design | EA design | 0 | 0 | 0
23.15 | Bent Plan and Elevation | Sheet | 0 | 0 | 0
23.16 | Bent Details | Sheet | 0 | 0 | 0
Pier Design and Plans
23.17 | Pier Geometry | EA pier | 0 | 0 | 0
23.18 | Pier Stability Analysis | EA design | 0 | 0 | 0
23.19 | Pier Structural Design | EA design | 0 | 0 | 0
23.2 | Pier Plan and Elevation | Sheet | 0 | 0 | 0
23.21 | Pier Details | Sheet | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
23.22 | Foundation Layout | Sheet | 0 | 0 | 0
Superstructure Deck Design and Plans
23.23 | Finish Grade Elevation (FGE) Calculation | LS | 1 | 0 | 0
23.24 | Finish Grade Elevations | Sheet | 0 | 0 | 0
23.25 | Bridge Deck Design | EA section | 0 | 0 | 0
23.26 | Bridge Deck Reinforcing and Concrete Quantities | EA Unit | 0 | 0 | 0
23.27 | Superstructure Plan | Sheet | 0 | 0 | 0
23.28 | Superstructure Section | Sheet | 0 | 0 | 0
23.29 | Miscellaneous Bridge Deck Details | Sheet | 0 | 0 | 0
Reinforcing Bar Lists
23.3 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0
Structural Steel Plate Girder Design
23.31 | Unit Modeling | EA Unit | 0 | 0 | 0
23.32 | Section Design | EA Unit | 0 | 0 | 0
23.33 | Stiffener Design and Locations | EA Unit | 0 | 0 | 0
23.34 | Cross-Frame Design | EA Unit | 0 | 0 | 0
23.35 | Connections | EA Unit | 0 | 0 | 0
23.36 | Bearing Assembly Design and Detailing (with Jacking Analysis) | EA Unit | 0 | 0 | 0
23.37 | Splice Design | EA Unit | 0 | 0 | 0
23.38 | Shear Stud Connectors | EA Unit | 0 | 0 | 0
23.39 | Deflection Analysis | EA Unit | 0 | 0 | 0
23.4 | Framing Plan | Sheet | 0 | 0 | 0
23.41 | Girder Elevation | Sheet | 0 | 0 | 0
23.42 | Structural Steel Details | Sheet | 0 | 0 | 0
23.43 | Splice Details | Sheet | 0 | 0 | 0
23.44 | Girder Deflections and Camber | Sheet | 0 | 0 | 0
Structural Steel Box Girder Design
23.45 | Unit Modeling | EA Unit | 0 | 0 | 0
23.46 | Section Design | EA Unit | 0 | 0 | 0
23.47 | Stiffener Design and Locations | EA Unit | 0 | 0 | 0
23.48 | Interior Cross-Frame Design | EA Unit | 0 | 0 | 0
23.49 | Exterior Cross-Frame Design | EA Unit | 0 | 0 | 0
23.5 | Connections | EA Unit | 0 | 0 | 0
23.51 | Bearing Assembly Design and Detailing (with Jacking Analysis) | EA Unit | 0 | 0 | 0
23.52 | Splice Design | EA Unit | 0 | 0 | 0
23.53 | Shear Stud Connectors | EA Unit | 0 | 0 | 0
23.54 | Deflection Analysis | EA Unit | 0 | 0 | 0
23.55 | Framing Plan | Sheet | 0 | 0 | 0
23.56 | Girder Elevation | Sheet | 0 | 0 | 0
23.57 | Structural Steel Details | Sheet | 0 | 0 | 0
23.58 | Splice Details | Sheet | 0 | 0 | 0
23.59 | Girder Deflections and Camber | Sheet | 0 | 0 | 0
Erection Scheme
23.6 | Erection scheme analysis | EA Critical Stage | 0 | 0 | 0
23.61 | Erection scheme | Sheet | 0 | 0 | 0
Load Rating
23.62 | Load Rating | EA Unit | 0 | 0 | 0
23. Structural Steel Bridge Total |  |  |  |  | 0

## 24. Movable Span Bridge
Project Activity 24: Movable Span Bridge
Task No. | Task | Unit | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
Final Design Bascule Pier
24.1 | Pier Deck | LS | 1 | 0 | 0
24.2 | Leaf/Pier Clearance Diagrams | EA Diagram | 0 | 0 | 0
24.3 | Load Shoe Columns | LS | 1 | 0 | 0
24.4 | Trunnion Columns | LS | 1 | 0 | 0
24.5 | Foundations | LS | 1 | 0 | 0
24.6 | Footing | LS | 1 | 0 | 0
24.7 | Seal | LS | 1 | 0 | 0
24.8 | Back Wall (Approach Span Bearings) Closed Piers Only | LS | 1 | 0 | 0
24.9 | Bascule Pier Deck Elevations | EA Pier | 0 | 0 | 0
Bascule Pier Dimensions - Detailing
24.1 | Pier Plan Views | Sheet | 0 | 0 | 0
24.11 | Pier Elevation Views | Sheet | 0 | 0 | 0
24.12 | Pier Sections | Sheet | 0 | 0 | 0
Bascule Pier Reinforcing Details
24.13 | Pier Reinforcing | Sheet | 0 | 0 | 0
Bascule Pier Miscellaneous Details
24.14 | Pier Barrier Details | Sheet | 0 | 0 | 0
24.15 | Stair Details | Sheet | 0 | 0 | 0
24.16 | Handrail Details | Sheet | 0 | 0 | 0
24.17 | Ladder and Hatch Details | Sheet | 0 | 0 | 0
24.18 | Pier Equipment | Sheet | 0 | 0 | 0
24.19 | Bascule Pier Notes and Summary of Quantities | Sheet | 0 | 0 | 0
24.2 | Miscellaneous Details | Sheet | 0 | 0 | 0
Bascule Leaf Design
24.21 | Deck Design | LS | 1 | 0 | 0
24.22 | Sidewalk Design | LS | 1 | 0 | 0
24.23 | Stringer Design | LS | 1 | 0 | 0
24.24 | Typical Floorbeam Design | LS | 1 | 0 | 0
24.25 | End Floorbeam Design | LS | 1 | 0 | 0
24.26 | Deep Floorbeam Design | LS | 1 | 0 | 0
24.27 | Sidewalk Bracket Design | LS | 1 | 0 | 0
24.28 | Roadway Bracket Design | LS | 1 | 0 | 0
24.29 | Main Girder Influence Lines | LS | 1 | 0 | 0
24.3 | Main Girder Design | LS | 1 | 0 | 0
24.31 | Trunnion Girder Design | LS | 1 | 0 | 0
24.32 | Main Girder Camber Data | LS | 1 | 0 | 0
24.33 | Leaf Lateral Bracing Design | LS | 1 | 0 | 0
24.34 | Counterweight Design | LS | 1 | 0 | 0
24.35 | Live Load Shoe Design | LS | 1 | 0 | 0
24.36 | Barrier Design | LS | 1 | 0 | 0
24.37 | Deck Elevations | LS | 1 | 0 | 0
24.38 | Balance Calculations | LS | 1 | 0 | 0
Bascule Leaf Detailing
24.39 | Bascule GP&E | Sheet | 0 | 0 | 0
24.4 | Bascule Leaf Notes | Sheet | 0 | 0 | 0
24.41 | Framing Plan | Sheet | 0 | 0 | 0
24.42 | Flooring Plan and Details | Sheet | 0 | 0 | 0
24.43 | Typical Section and Finish Grade Elevations | Sheet | 0 | 0 | 0
24.44 | Girder Elevation | Sheet | 0 | 0 | 0
24.45 | Girder Details | Sheet | 0 | 0 | 0
24.46 | Camber Layout | Sheet | 0 | 0 | 0
24.47 | Floor Beams | Sheet | 0 | 0 | 0
24.48 | Counterweight Girder/Box | Sheet | 0 | 0 | 0
24.49 | Trunnion Girder | Sheet | 0 | 0 | 0
24.5 | Cylinder Girder | Sheet | 0 | 0 | 0
24.51 | Lateral Bracing Details | Sheet | 0 | 0 | 0
24.52 | Counterweight Bracing Details | Sheet | 0 | 0 | 0
24.53 | Joint Details | Sheet | 0 | 0 | 0
24.54 | Traffic Barrier Details | Sheet | 0 | 0 | 0
24.55 | Pedestrian Rail and Support Details | Sheet | 0 | 0 | 0
24.56 | Curb and Sidewalk Details | Sheet | 0 | 0 | 0
24.57 | Barrier and Sidewalk Bracket Details | Sheet | 0 | 0 | 0
24.58 | Counterweight Details | Sheet | 0 | 0 | 0
24.59 | Stress Table or Influence Lines | Sheet | 0 | 0 | 0
Mechanical Design
24.6 | Final Power Requirements | LS | 1 | 0 | 0
24.61 | Trunnion Assembly | LS | 1 | 0 | 0
24.62 | Span Locks | LS | 1 | 0 | 0
24.63 | Sump Pumps | LS | 1 | 0 | 0
Mechanical Drive Design
24.64 | Drive Shafts, Couplings, Keys, Bearings and Supports | LS | 1 | 0 | 0
24.65 | Rack & Pinion, Bearings and Supports | LS | 1 | 0 | 0
24.66 | Drive Train | LS | 1 | 0 | 0
24.67 | Motor Brakes & Machinery Brakes | LS | 1 | 0 | 0
Hydraulic Drive Design
24.68 | Hydraulic Drive | LS | 1 | 0 | 0
Machinery Detailing
24.69 | Machinery Layout | Sheet | 0 | 0 | 0
24.7 | Machinery Elevation | Sheet | 0 | 0 | 0
24.71 | Machinery Section | Sheet | 0 | 0 | 0
24.72 | Trunnion Assembly | Sheet | 0 | 0 | 0
24.73 | Drive Details | Sheet | 0 | 0 | 0
24.74 | Span Locks | Sheet | 0 | 0 | 0
Electrical Design
24.75 | Load Analysis | LS | 1 | 0 | 0
24.76 | Power Distribution | LS | 1 | 0 | 0
24.77 | Drive Equipment | LS | 1 | 0 | 0
24.78 | Bridge Controls | LS | 1 | 0 | 0
24.79 | Grounding | LS | 1 | 0 | 0
24.8 | Lightning and Surge Suppression | LS | 1 | 0 | 0
24.81 | Pier Lighting | LS | 1 | 0 | 0
Electrical Detailing
24.82 | Electrical Plan and Elevation | Sheet | 0 | 0 | 0
24.83 | Electrical Symbols and Abbreviations | Sheet | 0 | 0 | 0
24.84 | Single/Three Line Diagram | Sheet | 0 | 0 | 0
24.85 | Panelboard and Light Fixture Schedules | Sheet | 0 | 0 | 0
24.86 | Wire and Conduit Schedules and Diagrams | Sheet | 0 | 0 | 0
24.87 | Control Desk/Panel Layout | Sheet | 0 | 0 | 0
24.88 | Control Schematics | Sheet | 0 | 0 | 0
24.89 | PLC Logic | Sheet | 0 | 0 | 0
24.9 | Communication System | Sheet | 0 | 0 | 0
24.91 | Navigation Lighting Details | Sheet | 0 | 0 | 0
24.92 | Pedestrian Gate, Traffic Gate and Barrier Details | Sheet | 0 | 0 | 0
24.93 | Submarine Cable | Sheet | 0 | 0 | 0
24.94 | Miscellaneous Details | Sheet | 0 | 0 | 0
Control House
24.95 | Architectural Design | LS | 1 | 0 | 0
24.96 | Architectural Details | Sheet | 0 | 0 | 0
24.97 | Structural Design | LS | 1 | 0 | 0
24.98 | Structural Details | Sheet | 0 | 0 | 0
24.99 | HVAC/Plumbing Design | LS | 1 | 0 | 0
24.1 | HVAC/Plumbing/Electrical Cables | Sheet | 0 | 0 | 0
Reinforcing Bar Lists
24.101 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0
Load Rating
24.102 | Load Ratings | LS | 1 | 0 | 0
24. Movable Span Bridge Total |  |  |  |  | 0

## 25. Retaining Walls
Project Activity 25: Retaining Walls
Task No. | Task | Unit | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
General Requirements
25.1 | Key Sheet | Sheet | 0 | 0 | 0
25.2 | Horizontal Wall Geometry | Per Wall | 0 | 0 | 0
Permanent Proprietary Walls
25.3 | Vertical Wall Geometry | Per Wall | 0 | 0 | 0
25.4 | Semi-Standard Drawings | Sheet | 0 | 0 | 0
25.5 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0
25.6 | Details | Sheet | 0 | 0 | 0
Temporary Proprietary Walls
25.7 | Vertical Wall Geometry | Per Wall | 0 | 0 | 0
25.8 | Semi-Standard Drawings | Sheet | 0 | 0 | 0
25.9 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0
25.1 | Details | Sheet | 0 | 0 | 0
Cast-in-Place Retaining Walls
25.11 | Design | EA Design | 0 | 0 | 0
25.12 | Vertical Wall Geometry | EA Wall | 0 | 0 | 0
25.13 | General Notes | Sheet | 0 | 0 | 0
25.14 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0
25.15 | Sections and Details | Sheet | 0 | 0 | 0
25.16 | Reinforcing Bar List | Sheet | 0 | 0 | 0
Other Retaining Walls and Bulkheads
25.17 | Design | EA Design | 0 | 0 | 0
25.18 | Vertical Wall Geometry | EA Wall | 0 | 0 | 0
25.19 | General Notes, Tables and Misc. Details | Sheet | 0 | 0 | 0
25.2 | Wall Plan and Elevations | Sheet | 0 | 0 | 0
25.21 | Details | Sheet | 0 | 0 | 0
25. Retaining Walls Total |  |  |  |  | 0

## 26. Structures-Miscellaneous
Project Activity 26: Structural - Miscellaneous
Task No. | Task | Unit | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
Concrete Box Culvert
26.1 | Concrete Box Culverts | EA | 0 | 0 | 0
26.2 | Concrete Box Culverts Extensions | EA Extension | 0 | 0 | 0
26.3 | Concrete Box Culvert Data Table Plan Sheets | Sheet | 0 | 0 | 0
26.4 | Concrete Box Culvert Special Details Plan Sheets | Sheet | 0 | 0 | 0
Strain Poles
26.5 | Steel Strain Poles | Initial Config | 0 | 0 | 0
|  | EA Add'l Config | 0 | 0 | 0
26.6 | Concrete Strain Poles | Initial Config | 0 | 0 | 0
|  | EA Add'l Config | 0 | 0 | 0
26.7 | Strain Pole Data Table Plan Sheets | Sheet | 0 | 0 | 0
26.8 | Strain Pole Special Details Plan Sheets | Sheet | 0 | 0 | 0
Mast Arms
26.9 | Mast Arms | EA Design | 0 | 0 | 0
26.1 | Mast Arms Data Table Plan Sheets | Sheet | 0 | 0 | 0
26.11 | Mast Arm Special Details Plan Sheets | Sheet | 0 | 0 | 0
Special Structures
26.12 | Fender System | LS | 1 | 0 | 0
26.13 | Fender System Access | LS | 1 | 0 | 0
26.14 | Special Structures | LS | 1 | 0 | 0
26.15 | Other Structures | LS | 1 | 0 | 0
26. Structures - Miscellaneous Total |  |  |  |  | 0

## 27. Landscape Analysis
Project Activity 27: Landscape Analysis
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
27.1 | Data Collection | LS | 1 | 0 | 0
27.2 | Inventory and Analysis | LS | 1 | 0 | 0
27.3 | Vegetation Disposition Plan | LF | 0 | 0 | 0
27.4 | Report Preparation | LS | 1 | 0 | 0
27.5 | Planting Design | LF | 0 | 0 | 0
27.6 | Irrigation Design | LF | 0 | 0 | 0
27.7 | Hardscape Design | LF | 0 | 0 | 0
27.8 | Quantites | EA | 0 | 0 | 0 | (LIST Submittals)
27.9 | Cost Estimates | EA | 0 | 0 | 0 | (LIST Submittals)
27.1 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
27.11 | Inspection Services | LS | 1 | 0 | 0
27.12 | Other Landscape Services | LS | 1 | 0 | 0
27.13 | Field Reviews | EA | 0 | 0 | 0 | (LIST)
27.14 | Technical Meetings | EA | 0 | 0 | 0 | (LIST)
27. Landscape Analysis Total |  |  |  |  | 0

## 28. Landscape Plans
Project Activity 28: Landscape Plans
Task No. | Task | Scale | Units | No. of Units | Hours/ Unit or Sheet | Total Hours | Comments
28.1 | Key Sheet |  | Sheet | 0 | 0 | 0
28.2 | Plant Schedule |  | Sheet | 0 | 0 | 0
28.3 | General Notes |  | Sheet | 0 | 0 | 0
28.4 | Tree and Vegetation Protection and Relocation Plans and Tree Disposition Plans |  | Sheet | 0 | 0 | 0
28.5 | Planting Plans |  | Sheet | 0 | 0 | 0
28.6 | Planting Details and Notes |  | Sheet | 0 | 0 | 0
28.7 | Irrigation Plans |  | Sheet | 0 | 0 | 0
28.8 | Irrigation Details and Notes |  | Sheet | 0 | 0 | 0
28.9 | Hardscape Plans |  | Sheet | 0 | 0 | 0
28.1 | Hardscape Details and Notes |  | Sheet | 0 | 0 | 0
28.11 | Maintenance Plan |  | Sheet | 0 | 0 | 0
28. Landscape Plans Total | [5 empty] | 0

## 29. Architectural
Project Activity 29: Architectural
Task No. | Task | Scale | Units | No of Units | Hours/ Unit or Sheet | Total Hours | Comments
Architectural Plans
29.1 | Key Sheet and Index of Sheets |  | Sheet | 0 | 0 | 0
29.2 | General Notes, Abbreviations, Symbols, and Legend |  | Sheet | 0 | 0 | 0
29.3 | Site Plans |  | Sheet | 0 | 0 | 0
29.4 | Floor Plans (Small Scale) |  | Sheet | 0 | 0 | 0
29.5 | Floor Plans (Large Scale) |  | Sheet | 0 | 0 | 0
29.6 | Exterior Elevations |  | Sheet | 0 | 0 | 0
29.7 | Roof Plans |  | Sheet | 0 | 0 | 0
29.8 | Roof Details |  | Sheet | 0 | 0 | 0
29.9 | Interior Elevations |  | Sheet | 0 | 0 | 0
29.1 | Rest Room Plans (Enlarged) |  | Sheet | 0 | 0 | 0
29.11 | Rest Room Elevations |  | Sheet | 0 | 0 | 0
29.12 | Building Sections |  | Sheet | 0 | 0 | 0
29.13 | Stair Section, Enlarged Stair Plan and Details |  | Sheet | 0 | 0 | 0
29.14 | Reflective Ceiling Plans |  | Sheet | 0 | 0 | 0
29.15 | Room Finish Schedule or Finish Plan |  | Sheet | 0 | 0 | 0
29.16 | Door and Window Schedule |  | Sheet | 0 | 0 | 0
29.17 | Door Jamb Details and Window Details |  | Sheet | 0 | 0 | 0
29.18 | Exterior Wall Sections |  | Sheet | 0 | 0 | 0
29.19 | Interior Wall Sections |  | Sheet | 0 | 0 | 0
29.2 | Overhead Door Details |  | Sheet | 0 | 0 | 0
29.21 | Curtain Wall Details |  | Sheet | 0 | 0 | 0
29.22 | Fascia, Soffit and Parapet Details |  | Sheet | 0 | 0 | 0
29.23 | Signage Details |  | Sheet | 0 | 0 | 0
29.24 | Miscellaneous Details |  | Sheet | 0 | 0 | 0
29.25 | Repetitive Sheets |  | Sheet | 0 | 0 | 0
29.26 | Design Narrative Reports |  | LS | 1 | 0 | 0
29.27 | Permitting |  | EA | 0 | 0 | 0 | (LIST)
29.28 | Other Pertinent Project Documentation |  | LS | 1 | 0 | 0
29.29 | Cost Estimate |  | EA | 0 | 0 | 0 | (LIST)
29.3 | Technical Special Provisions and Modified Special Provisions Packages |  | LS | 1 | 0 | 0
29.31 | Field Reviews |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
29.32 | Technical Meetings |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
Architectural Plans Total | [5 empty] | 0
Structural Plans
29.33 | General Notes, Abbreviations, Symbols, and Legend |  | Sheet | 0 | 0 | 0
29.34 | Foundation Plans (Small Scale) |  | Sheet | 0 | 0 | 0
29.35 | Foundation Plans (Large Scale) |  | Sheet | 0 | 0 | 0
29.36 | Slab Plans (Small Scale) |  | Sheet | 0 | 0 | 0
29.37 | Slab Plans (Large Scale) |  | Sheet | 0 | 0 | 0
29.38 | Slab Placement Plans |  | Sheet | 0 | 0 | 0
29.39 | Slab Placement Details |  | Sheet | 0 | 0 | 0
29.4 | Foundation Sections |  | Sheet | 0 | 0 | 0
29.41 | Foundation Details |  | Sheet | 0 | 0 | 0
29.42 | Slab Sections |  | Sheet | 0 | 0 | 0
29.43 | Slab Details |  | Sheet | 0 | 0 | 0
29.44 | Roof Framing Plans (Small Scale) |  | Sheet | 0 | 0 | 0
29.45 | Roof Framing Plans (Large Scale) |  | Sheet | 0 | 0 | 0
29.46 | Roof Loading Plans and Details |  | Sheet | 0 | 0 | 0
29.47 | Roof Sections |  | Sheet | 0 | 0 | 0
29.48 | Roof Details |  | Sheet | 0 | 0 | 0
29.49 | Bearing Wall Sections |  | Sheet | 0 | 0 | 0
29.5 | Bearing Wall Details |  | Sheet | 0 | 0 | 0
29.51 | Column Sections |  | Sheet | 0 | 0 | 0
29.52 | Column Details |  | Sheet | 0 | 0 | 0
29.53 | Miscellaneous Sections |  | Sheet | 0 | 0 | 0
29.54 | Repetitive Sheets |  | Sheet | 0 | 0 | 0
29.55 | Other Pertinent Project Documentation |  | LS | 1 | 0 | 0
29.56 | Cost Estimate |  | EA | 0 | 0 | 0 | (LIST Submittals)
29.57 | Technical Special Provisions and Modified Special Provisions Packages |  | LS | 1 | 0 | 0
29.58 | Field Reviews |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
29.59 | Technical Meetings |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
Structural Plans Total | [5 empty] | 0
Mechanical Plans
29.6 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  | Sheet | 0 | 0 | 0
29.61 | Plans (Small Scale) |  | Sheet | 0 | 0 | 0
29.62 | Plans (Large Scale) |  | Sheet | 0 | 0 | 0
29.63 | Details |  | Sheet | 0 | 0 | 0
29.64 | Sections |  | Sheet | 0 | 0 | 0
29.65 | Piping Schematics |  | Sheet | 0 | 0 | 0
29.66 | Control Plans |  | Sheet | 0 | 0 | 0
29.67 | Schedules |  | Sheet | 0 | 0 | 0
29.68 | HVAC Calculations |  | Sheet | 0 | 0 | 0
29.69 | Life Cycle Cost Analysis |  | Sheet | 0 | 0 | 0
29.7 | Repetitive Sheets |  | LS | 1 | 0 | 0
29.71 | Other Pertinent Project Documentation |  | LS | 1 | 0 | 0
29.72 | Cost Estimate |  | EA | 0 | 0 | 0 | (Submittals)
29.73 | Technical Special Provisions and Modified Special Provisions Packages |  | LS | 1 | 0 | 0
29.74 | Field Reviews |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
29.75 | Technical Meetings |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
Mechanical Plans Total | [5 empty] | 0
Plumbing Plans
29.76 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  | Sheet | 0 | 0 | 0
29.77 | Plans (Small Scale) |  | Sheet | 0 | 0 | 0
29.78 | Plans (Large Scale) |  | Sheet | 0 | 0 | 0
29.79 | Isometrics (Large Scale) |  | Sheet | 0 | 0 | 0
29.8 | Riser Diagrams |  | Sheet | 0 | 0 | 0
29.81 | Details |  | Sheet | 0 | 0 | 0
29.82 | Repetitive Sheets |  | Sheet | 0 | 0 | 0
29.83 | Other Pertinent Project Documentation |  | LS | 1 | 0 | 0
29.84 | Cost Estimate |  | EA | 0 | 0 | 0 | (LIST Submittals)
29.85 | Technical Special Provisions and Modified Special Provisions Packages |  | LS | 1 | 0 | 0
29.86 | Field Reviews |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
29.87 | Technical Meetings |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
Plumbing Plans Total | [5 empty] | 0
Fire Protection Plans
29.88 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  | Sheet | 0 | 0 | 0
29.89 | Fire Protection Plan |  | Sheet | 0 | 0 | 0
29.9 | Riser Diagram, Details, and Partial Plans |  | Sheet | 0 | 0 | 0
29.91 | Hydraulic Calculation |  | Sheet | 0 | 0 | 0
29.92 | Repetitive Sheets |  | Sheet | 0 | 0 | 0
29.93 | Other Pertinent Project Documentation |  | LS | 1 | 0 | 0
29.94 | Cost Estimate |  | EA | 0 | 0 | 0 | (LIST Submittals)
29.95 | Technical Special Provisions and Modified Special Provisions Packages |  | LS | 1 | 0 | 0
29.96 | Field Reviews |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
29.97 | Technical Meetings |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
Fire Protection Plans Total | [5 empty] | 0
Electrical Plans
29.98 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  | Sheet | 0 | 0 | 0
29.99 | Electrical Site Plan |  | Sheet | 0 | 0 | 0
29.1 | Lighting Plans |  | Sheet | 0 | 0 | 0
29.101 | Lighting Fixtures Schedules |  | Sheet | 0 | 0 | 0
29.102 | Lighting Fixtures Details |  | Sheet | 0 | 0 | 0
29.103 | Lightning Protection Plans |  | Sheet | 0 | 0 | 0
29.104 | Lightning Protection Details |  | Sheet | 0 | 0 | 0
29.105 | Power Plans |  | Sheet | 0 | 0 | 0
29.106 | Power Distribution Riser Diagrams |  | Sheet | 0 | 0 | 0
29.107 | Panel Board Schedules |  | Sheet | 0 | 0 | 0
29.108 | Data Plans |  | Sheet | 0 | 0 | 0
29.109 | Data Details |  | Sheet | 0 | 0 | 0
29.11 | Communication Plans |  | Sheet | 0 | 0 | 0
29.111 | Communication Details |  | Sheet | 0 | 0 | 0
29.112 | Security Alarm System Plans |  | Sheet | 0 | 0 | 0
29.113 | Miscellaneous Details |  | Sheet | 0 | 0 | 0
29.114 | Repetitive Sheets |  | LS | 1 | 0 | 0
29.115 | Energy Analysis |  | LS | 1 | 0 | 0
29.116 | Other Pertinent Project Documentation |  | LS | 1 | 0 | 0
29.117 | Cost Estimate |  | EA | 0 | 0 | 0 | (LIST Submittals)
29.118 | Technical Special Provisions and Modified Special Provisions Packages |  | LS | 1 | 0 | 0
29.119 | Field Reviews |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
29.12 | Technical Meetings |  | EA | 0 | 0 | 0 | (LIST Quantity & Number of Attendees)
Electrical Plans Total | [5 empty] | 0
29.121 | LEED Certification |  | LS | 1 | 0 | 0
31. Architecture Development Total | [5 empty] | 0